## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assign To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Shaik Farshad | 11-10-2026 | Correct AI responses may receive unexpectedly low evaluation scores that do not reflect their actual relevance and factual correctness. | Sprint 4 | Shaik Farshad | Scoring Logic | Review dimension-wise scoring, final score aggregation, default values, and verdict mapping. Retest with known correct and incorrect responses. | Pending | Open | Root cause and permanent fix require verification.
2 | Shaik Farshad | 11-10-2026 | Different AI responses may repeatedly receive the same overall score (for example, 32.7), even when response quality differs. | Sprint 4 | Shaik Farshad | Score Aggregation | Compare individual dimension scores and trace the calculation path to identify hardcoded values, stale results, or aggregation errors. | Pending | Open | Confirm reproducibility and retest after correction.
3 | Shaik Farshad | 11-10-2026 | Validate whether the Hallucination Detection Agent correctly distinguishes claims supported by the reference knowledge base from unsupported claims. | Sprint 4 | Shaik Farshad | Hallucination Detection | Test supported and unsupported claims against reference evidence and inspect the agent's evidence matching and scoring logic. | Pending | Open | Validation required; record as a confirmed defect only if reproduced.
4 | Shaik Farshad | 11-10-2026 | Verify that Relevance, Accuracy, Hallucination, and Completeness scores accurately reflect the submitted response. | Sprint 4 | Shaik Farshad | Agent Evaluation | Run test cases for each evaluation dimension and compare the returned scores with expected outcomes. | Pending | Open | Validation required; attach test case results when available.
5 | Shaik Farshad | 11-10-2026 | Check whether the dashboard displays accurate pass/fail rates, average dimension scores, hallucination frequency, and quality trends. | Sprint 4 | Shaik Farshad | Dashboard / Analytics | Compare dashboard metrics with the underlying evaluation history and verify that charts refresh after new evaluations. | Pending | Open | Confirm data consistency before marking complete.
6 | Shaik Farshad | 11-10-2026 | Check whether the exported PDF report contains correct scores, final verdict, dimension-wise explanations, evidence, and improvement suggestions. | Sprint 4 | Shaik Farshad | Report Generation | Export sample evaluation reports and compare all displayed fields with the original evaluation result. | Pending | Open | Validation required; update after export testing.

## Read Me
AI Response Validation System – Defect Tracker
Purpose | Track observed or suspected defects in the AI response evaluation project.
Important | Rows 3–6 describe validation checks. Keep them only if relevant to your actual project; do not report untested issues as confirmed defects.
Status guidance | Use Open until a defect is fixed and successfully retested. Use Closed only after verification.
Action Taken Date | Enter the actual date when the corrective action is completed; do not use a future or invented completion date.
Date note | Submitted Date is set to 11-10-2026 as the preparation date. Change it if your actual submission/report date differs.